## Overview
DLSU Software Engineering
CSSWENG
CSSWENG GRP-1 S13
TEST SCRIPT
Team # | 1 | Success Rate Overview
Section | S13 |  | Pass | Fail | Pass Rate
Members
| Ferrer, Angel June | 00-Running the Program | 2 | 0 | 100%
| Ferrer, Angel June | 01-Login | 7 | 0 | 100%
| Ferrer, Angel June | 02-UI Review | 7 | 0 | 100%
| Marinas, Carl Mervyn G. | 03-Admin Functions | 10 | 0 | 100%
| Marinas, Carl Mervyn G. | 04-SDW Functions | 8 | 0 | 100%

## 00-Running the Program
Test ID | 00-Running the Program
Designed by | Ferrer, Angel
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To test if the program runs
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed
1 | Server should start and listen on port 3000 | In the command prompt of the project directory: 1. Type "node app.js" 2. Then enter | - Upon entering the command, the command prompt should display: Server is running on http://localhost:3000 -It should also display seeded users for testing | It showed the following informtaion: - Server is running on http://localhost:3000 - Seeded users | Pass | Ferrer, Angel | 2025-11-11
2 | Displaying login page | In the command prompt of the project directory: 1. ctrl + Click the displayed link of the localhost | - Upon doing the command: - It should redirect the user to the login page | It showed the following informtaion: - redirection to the login page | Pass | Ferrer, Angel | 2025-11-11

## 01-Login
Test ID | 01-Login
Designed by | Chu, Andre Benedict & Ferrer, Angel June
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To test the overall functionality of the Login process
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed | Notes
1 | Login with valid credentials | In the Login Screen, the user should: 1. Enter a seeded account: - Username: admin1@gmail.com - Password: password123 2. Click the Login button | - Upon completing the test steps, the user should be redirected to the home page - A display in the command prompt that displays account credentials | Actual results displayed the following information: - User was redirected to the home page - Account credentials were displayed in the command prompt | Pass | Ferrer, Angel | 2025-11-12
2 | Login with invalid credentials | In the Login Screen, the user should: 1. Enter a non-seeded account: - Username: test_inv@gmail.com - Password: wrongpass123 2. Click the Login button | - Upon completing the test steps, the user should not be redirected to the home page - A display in the command prompt that: No Account Found - The user remains in the login page - User should be prompted that they have entered 'a wrong email address or password' | Actual results displayed the following information: - User is not redirected to the home page - No account was displayed in the command prompt - User remains in the login page | Pass | Ferrer, Angel | 2025-11-12 | User remained in the log in page but no prompt
3 | Login with empty fields | In the Login Screen, the user should: 1. Enter nothing 2. Click the Login button | - Upon completing the test steps, the user should not be redirected to the home page - Nothing is displayed in the command prompt - A prompt will appear on the log-in page that says "Please fill out this field." | Actual results displayed the following information: - User is not redirected to the home page and user remains in the login page - Nothing was displayed in the command prompt | Pass | Ferrer, Angel | 2025-11-12
Specific Test Scenarios / Edge Cases
4 | Logging with inputs of special characters: /<>[]{}+_-=!@#$%^&*() | In the Login Screen, the tester inputs: Username: #$%^{[()]} Password: ""&&^^## | The tester should not be accepted by the website. These should also not affect the state of the login page (Nothing Breaking). | Actual results displayed the following information: -User remains in the login page - A prompt appeared asking the user to put an '@' in the email field - When '@' was added, a prompt appeared saying there is a missing part | Pass | Ferrer, Angel | 2025-11-12
5 | Logging with inputs of all numbers | In the Login Screen, the tester inputs: Username: 6701830 Password: 9704631 | The tester should not be accepted by the website. These should also not affect the state of the login page (Nothing Breaking). | Actual results displayed the following information: -User remains in the login page - A prompt appeared asking the user to put an '@' in the email field - When '@' was added, a prompt appeared saying there is a missing part | Pass | Ferrer, Angel | 2025-11-12
6 | Concurrent Logins | The tester will open 3-5 tabs after running app.js. In these tabs, the tester will log current seeded accounts to test what will happen to the website | The tester should be accepted by the website for all accounts when logged in. The sessions should be independent. No data corruption should happen. | Both successfully logged in simultaneously | Pass | Ferrer, Angel | 2025-11-12
7 | Login then logout | In the Login Screen, the user should: 1. Enter an account from the database: - Username: admin1@gmail.com - Password: password123 2. Click the Login button 3. Click logout button after redirection | Upon completing the test steps the following should happen: - After login, user is redirected to the home page - After clicking the logout button in the home page, user is redirected to the login page | Actual results displayed the following information: - User was redirected to the home page after login - User was redirected to login page | Pass | Ferrer, Angel | 2025-11-12

## 02-UI Review
Test ID | 02- UI Review
Designed by | Ferrer, Angel June E.
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To verify that each page displays all required UI elements correctly.
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed
ADMIN
1 | Admin Homepage loads correctly with all required UI elements | Navigate to the Admin Homepage. Observe the layout and available UI elements. | – The Admin Homepage displays the following: • Header showing “Welcome, Admin <Name>!” • Four SPU buttons: AMP, FDQ, MPH, MS • Center message: “Click on an SPU to view SDWs assigned” • Logout button | – Header “Welcome, Admin Admin!” was displayed – SPU buttons (AMP, FDQ, MPH, MS) appeared – Center message shown correctly – Logout button visible | Pass | Ferrer, Angel June | 2025-11-12
2 | From the Admin Homepage, click AMP. | From the Admin Homepage, click AMP. | – System redirects to the AMP SPU page (/admin/spu/AMP). – The page displays the following: • Header: “Welcome to Supervisor Suite!” • Subheader: “SDWs Assigned For AMP” • Buttons: Create New Account, Back to SPUs, Logout | -User was redirected to /admin/spu/AMP. – Header and subheader displayed correctly. – Create New Account, Back to SPUs, and Logout buttons were visible. | Pass | Ferrer, Angel June | 2025-11-12
SDW
3 | SDW Homepage loads correctly with all required UI elements | Navigate to the SDW Homepage after logging in. Observe the available report categories and the upload area. | The SDW Homepage displays the following: DSWD Annual Report – Community Profile – Target Vs ACC & SE – Caseload Masterlist – Education Profile – Assistance to Families – Poverty Stoplight – CNF Candidates – Retirement Candidates – VM Accomplishments – Correspondence – Leaders Directory • A large upload box in the center with the label “drop files here” • A Logout button at the bottom right | – Report category buttons were visible on the left sidebar – The center upload box with “drop files here” was displayed – Logout button was visible | Pass | Ferrer, Angel June | 2025-11-12
4 | SDW Report Category Pages load correctly when a sidebar option is clicked | Navigate to the SDW Homepage after logging in. Select any report category from the left sidebar (e.g., DSWD Annual Report, Community Profile, Target vs ACC & SE, etc.). Observe the layout and visible elements. | The selected report page displays the following: • Header showing the correct category name. • Sidebar with all SDW report buttons still visible. • “Sort By” dropdown on the upper-right corner. • “Back to Upload Page” button below the header. • Main content area showing either report files or the message “No reports found.” • Logout button visible on the lower-right corner. | Report page loaded successfully. Correct header was displayed. Sidebar, Sort By dropdown, Back to Upload button, and Logout button were visible. | Pass | Ferrer, Angel June | 2025-11-18
5 | Successful file upload shows confirmation modal | .Drag and drop or select a valid file (e.g., .xlsx).Wait for the upload to process. | Drag and drop or select a valid file (e.g., .xlsx). Wait for the upload to process. | - A confirmation modal appears. - Modal displays: “Your file <filename> has successfully been uploaded to <Report Category>”. - Buttons Continue and Upload Another File are visible and clickable. | Pass | Ferrer, Angel June | 2025-11-18
SUPER VISOR
6 | SuperVisor Homepage loads correctly with all required UI elements | Navigate to the Supervisor Homepage. Observe the layout and visible elements. | – The Supervisor Homepage displays the following: • Header showing “Welcome, Supervisor <Name>!” • Subheader “SDWs Assigned:” • Sort dropdown on the right (Alphabetical) • Sidebar with system logo • Logout button at the lower-right corner | – Header “Welcome, Supervisor Jenny Parker!” was displayed – Subheader “SDWs Assigned:” was visible – Sort dropdown appeared on the right side – Sidebar with logo was displayed – Logout button was visible at the bottom-right | Pass | Ferrer, Angel June | 2025-11-18
7 | Supervisor can view the selected SDW’s full records page | After logging in as Supervisor, the user must: 1. Navigate to the Supervisor Homepage. 2. Select any SDW from the “SDWs Assigned” list. 3. Click on the SDW’s name. | Upon completing the steps, the system must redirect the user to the SDW Records Page showing: • The Supervisor greeting header (e.g., “Welcome, Supervisor Jenny Parker!”) • The SDW’s full name and SPU (e.g., “SDW – Marcus Aurelio’s Records”) • Report category buttons (DSWD Annual Report, Community Profile, Target Vs ACC & SE, etc.) • Sort dropdown for report categories • Back to SDWs Page button | the system correctly redirected the supervisor to the chosen SDW’s record view. The SDW name, complete report categories, Sort dropdown, and “Back to SDWs Page” button were all visible exactly as expected. | Pass | Ferrer, Angel June | 2025-11-18

## 03-Admin Functions
Test ID | 02-Admin Functions
Designed by | Marinas, Carl Mervyn
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To test the overall functionality of the Registration Process
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed
1 | All required registration fields are present | In the Register Screen, the tester should: 1. Check for the following input fields: Email, Password, and User type 2. Check if all input fields have the attribute 'required' and are empty | - Upon completing the steps above, the register page must contain the input fields for email, password, and user type - Verify that the input fields contain the attribute 'required' | It showed Registration page with the following information: - Input fields for email, password, and user type - Position is Tester - No company is shown | Pass | Marinas, Carl Mervyn | 2025-11-12
2 | Register will empty fields | In the Regiser Screen, the tester should: 1. Empty the input fields, if they arent already (if possible) 2. Click on the 'Register' button | - Upon completing the steps above, the tester should still be in the Register screen. - Verify that the following error message is shown: “Please fill out this field” | - After clickicking register, the current page is still the registration page - An error message was prompted with the message: "Please fill out this field" | Pass | Marinas, Carl Mervyn | 2025-11-12
3 | Select different user types | In the Register Screen, the tester should: 1. Select different user types 2. Check if types 'Supervisor' and 'SDW' are present | - Upon completing the steps above, the user should be able to select different types of user to register - Verify that the user types ' Supervisor' and 'SDW' are present | - The user was able to select different types of user - User types 'Supervisor' and 'SDW' are present | Pass | Marinas, Carl Mervyn | 2025-11-12
4 | Login as admin and register an account | In the Login Screen, the user should: 1. Enter a seeded admin account: - Username: admin1@gmail.com - Password: password123 2. Click the Login button 3. Click the create an account link 4. Enter a new account: - Username: new_acc17@gmail.com - Password: new_acc_pass - User Type: Supervisor or SDW 5. Submit new account | Upon completing the test steps the following should happen: - After login, user is redirected to the home page - After clicking the create an account link, registration fields should display - After submitting registration, user will be directed back to the home page | Actual results displayed the following information: - User was redirected to the home page after login - User was redirected to registration page after clicking the link - User was redirected to home page after submitting | Pass | Marinas, Carl Mervyn | 2025-11-12
Specific Test Scenarios / Edge Cases
5 | Register with inputs of special characters: /<>[]{}+_-=!@#$%^&*() | In the admin page, the tester inputs: Username: #$%^{[()]}@gmail.com Password: ""&&^^## user type: SDW | The accounts should not register into the database. These should also not affect the state of the registration page (Nothing Breaking). | - The admin is unable to register | Pass | Marinas, Carl Mervyn | 2025-11-14
6 | Register with inputs of all numbers | In the admin page, the tester inputs: Username: 6701830@gmail.com Password: 9704631 user type: Supervisor | The accounts should not register into the database. These should also not affect the state of the login page (Nothing Breaking). |  | Pass | Marinas, Carl Mervyn | 2025-11-14
7 | Concurrent Register | The tester will open 3-5 tabs after running app.js. After successfully logging in as the administrator, the tester will create 3-5 valid accounts. | All the accounts created by the tester as the admin should properly register in the database. No data corruption should happen. | - All accounts were registered. This is validated by the newly registered accounts being visible under the Supervisor page in admin | Pass | Marinas, Carl Mervyn | 2025-11-14
8 | Duplicate Register | 1. In the admin page, the tester selects any supervisor and clicks on "Create new account" and inputs the following: - First Name: Dummy - Middle Name: Test - Last Name: Account - Email Address: dummy_acc@gmail.com - Password: 1234 - SPU: MS 2. Then click create account 3. The tester then exactly repeats step 1 & 2 | - Upon completing the steps 1 & 2, the user should be able to successfully create a new account. - Upon performing step 3, when clicking "create account" the web app should throw an error stating that a account already exists with the same email address. | - The user is prompted with an error stating that there exists an account with the inputted email | Pass | Marinas, Carl Mervyn | 2025-11-14
9 | Edit a SDW profile | In the admin page, the tester must: 1. Select a type of supervisor - Select MS 2. Click edit beside a SDW user - Select edit on user Dummy 3. Change the first name, password, and SPU - Change name Dummy -> Dummyy - Input "1234" for password - Change SPU from MS -> AMP 4. Click confirm edits | Upon completing the steps the following should happen: - The user's first name, password, and profile picture has been updated - While still logged in as admin, the user must see that the updated user is now under AMP supervisor from MS - The name of the edited user account should be the newly edited name - The user will now log in with a new password different from the previous one | - The updated user account is visible in the under the new supervisor and no longer visible in the previous - The user's first name is also updated with what was edited - Loging in withe the edited user's account will now requre the new edited password | Pass | Marinas, Carl Mervyn | 2025-11-14
10 | Delete a SDW profile | In the admin page, the user must: 1. Register a new account - First name: Temp - Middle Name: Del - Last Name: Account - Email: deltest@gmail.com - Password: 1234 - SPU: MPH 2. Log out of admin account, log in to the newly created account and upload a report 3. Log out of the SDW account and log back in to the admin account, navigate to the MPH tab 3. For user Temp, click on delete 4. Confirm delete | Upon completing the steps, the user should observe that: - The user "Temp" no longer exist under MPH supervisor - Can no longer login using the registered email and password - Any reports uploaded by the user should transfer to the admin account | - There is no prompt for confirming delete - User no longer exists in the system | Pass | Marinas, Carl Mervyn | 2025-11-14

## 04-SDW Functions
Test ID | 04 - SDW Functions
Designed by | Chu, Andre Benedict & Marinas, Carl Mervyn
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To test the functionality of the file uploading that the sdws will be doing.
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed
1 | File uploads made should register in the database (Assuming that we are currently using a local database). | In the home page of the SDW, the tester should: 1. Click on the "drop files here" button to upload 2. User selects a file 3. The user then selects the correct type of report and clicks confirm - For this test, user selects Community Profile | Upon completing the steps, the uploaded file should appear under the Community Profile page of the user. Upon clicking the file, a preview is shown with options to download or delete | The file was successfully uploaded and is visible under the Community Profile Reports page. Looking at the local database, we can see the newly uploaded file, encrypted for security purposes. | Pass | Marinas, Carl Mervyn | 2025-11-14
2 | File upload of valid files | In the home page of the SDW, the tester should: 1. Click on the "drop files here" button to upload 2. User selects a Excel file 3. The user then selects the correct type of report and clicks confirm - For this test, user selects Community Profile | Upon completing the steps, the uploaded Excel report file should appear under the Community Profile page of the user. Upon clicking the file, a preview is shown with options to download or delete | The Excel Report file was successfully uploaded and is visible under the Community Profile Reports page | Pass | Marinas, Carl Mervyn | 2025-11-14
3 | File upload of invalid files | In the home page of the SDW, the tester should: 1. Click on the "drop files here" button to upload 2. User selects a non-Excel file - For this, user uploads a PDF file 3. The user then selects the correct type of report and clicks confirm - For this test, user selects Community Profile | Upon completing the steps, after the user selects the file a prompt is shown telling the user that the selected file is invalid and must select a Excel file. The confirm button also should be locked/unable to click | When selecting a file, it does not allow the user to select any other file extensions other than .xls or .xlsx. An error message is prompted if the user attempts to upload a file other than xls or xlsx. | Pass | Marinas, Carl Mervyn | 2025-11-14
Specific Test Scenarios / Edge Cases
4 | Tester uploads an image | In the home page of the SDW, the tester should: 1. Click on the "drop files here" button to upload 2. User selects a PNG file 3. The user then selects the correct type of report and clicks confirm - For this test, user selects Education Profile | Upon completing the steps, after the user selects the file a prompt is shown telling the user that the selected file is invalid and must select a Excel file. The confirm button also should be locked/unable to click | When selecting a file, it does not allow the user to select any other file extensions other than .xls or .xlsx. An error message is prompted if the user attempts to upload a file other than xls or xlsx. | Pass | Marinas, Carl Mervyn | 2025-11-14
5 | Tester uploads a CSV or TSV file | In the home page of the SDW, the tester should: 1. Click on the "drop files here" button to upload 2. User selects a CSV file 3. The user then selects the correct type of report and clicks confirm - For this test, user selects Retirement Candidates | Upon completing the steps, after the user selects the file a prompt is shown telling the user that the selected file is invalid and must select a Excel file. The confirm button also should be locked/unable to click | When selecting a file, it does not allow the user to select any other file extensions other than .xls or .xlsx. An error message is prompted if the user attempts to upload a file other than xls or xlsx. | Pass | Marinas, Carl Mervyn | 2025-11-14
6 | Tester downloads a report file | After performing Test case 2, the user must: 1. Navigate to the Community profile page 2. Click on the uploaded Excel report File 3. Click on Download | Upon completing the steps, the user must be able to download the selected report to the specified download location in their system. This file should match the original file uploaded and not have been tampered/changed. | The Excel report file was successfully downloaded and matched the original file before uploading. No changes were made to the downloaded file. | Pass | Marinas, Carl Mervyn | 2025-11-14
7 | Tester deletes a report file | After performing Test case 2, the user must: 1. Navigate to the Community profile page 2. Click on the uploaded Excel report File 3. Click on Delete | Upon completing the steps, the user must be able to see that the report has now been deleted from the Community Profile tab. | The Excel report file was sccessfully deleted from the system and is verifiable by it no longer being present in the Community Profile Reports page | Pass | Marinas, Carl Mervyn | 2025-11-14
8 | Multiple Files are uploaded | After performing the SDW upload flow, the user must: 1. Select multiple files at once from the upload window. 2. Attempt to upload all selected files. | Upon completing the steps, the system must only upload the first file from the multiple selected. A success modal appears for that file only. The remaining files must not be uploaded. | The system successfully accepted only the first file from the multi-file selection. The upload confirmation modal appeared for the first file, and no additional uploads were processed. | Pass | Ferrer, Angel June | 2025-11-18

## 05- Supervisor Functions
Test ID | 05 - Supervisor Functions
Designed by | Ferrer, Angel June
Story/Module | No Designation by Prod
Test Data Source | User data entry
Objective(s) | To test the functionality of the file uploading that the supervisors will be doing.
Test Case # | Description | Test Steps | Expected Results | Actual Results | Pass or Fail | Performed by | Date Performed
1 | Supervisor can view all assigned SDWs and access their reports | After logging in as Supervisor, the user must: 1. Navigate to the Supervisor Homepage. 2. View the list of all SDWs assigned under the “SDWs Assigned” section. 3. Click on any SDW from the list. 4. Observe the report categories displayed for that SDW. | Upon completing the steps, • All SDWs assigned to the Supervisor must be visible. • When an SDW is selected, the system must redirect to the SDW Records Page. • The SDW Records Page must show all report categories | All assigned SDWs appeared correctly. Clicking an SDW successfully redirected to the SDW Records Page showing the full list of report categories, the Sort dropdown, and the Back to SDWs Page button. All elements matched the expected design and layout. | Pass | Ferrer, Angel June E. | 2025-11-18
2 | Supervisor can download reports uploaded by SDW | After selecting an SDW from the Supervisor Homepage, the user must: 1. Navigate to the SDW’s report categories page. 2. Click on any report category containing uploaded files. 3. Select an uploaded Excel report file. 4. Click the Download button. | Upon completing the steps, • The selected Excel report file should immediately begin downloading to the Supervisor’s device. • The downloaded file should match the exact filename and content uploaded by the SDW. • No errors or interruptions should occur during the download. | The Supervisor was able to successfully download the Excel report file without errors. The file downloaded with the correct filename and contained identical data to the SDW’s uploaded version. | Pass | Ferrer, Angel June E. | 2025-11-18
3 | Supervisor can delete uploaded reports from an SDW | After selecting an SDW from the Supervisor Homepage, the user must: 1. Navigate to the SDW’s report categories page. 2. Click on any report category containing uploaded Excel reports. 3. Select the uploaded Excel file. 4. Click the Delete button. | Upon completing the steps, • The selected Excel report must be removed from the SDW’s report category page. • The deleted file must no longer appear in the list of available reports. • No error messages should appear, and the page should update properly. | The Excel report was successfully deleted and was no longer visible in the SDW’s report category. The page updated with no errors, confirming the file was removed from the system. | Pass | Ferrer, Angel June E. | 2025-11-18
Specific Test Scenarios / Edge Cases